## Slide 1: Fingerprint based ATM Machine
PROJECT COM PLETION REPORT
Kiruthiga Ravindran

## Slide 2: PROJECT RECAP
The aim of the project is to ensure utmost security to the ATM’s by using fingerprint authentication.
Tasks Accomplished So far
Development of databases to store Fingerprints
Design of Sensors
Image Processing

## Slide 3: Current Status
Sprint 4 – Integration
Sprint 5 – Connecting implementation of storage, Testing
Out of the 12K machines – 1200 machines are taken based on the area and the fingerprint sensors are installed and tested extensively
After that, customers are allowed to use the facility and feedback will be collected.

## Slide 4: Customer Satisfaction Survey
The 1200 ATM branches customers are asked for ‘volunteer survey’ to rate the satisfaction of the customers.
Lots of factors such as ease of use, sense of security, changes required, and suggestions are taken into account to conclude the rating.
The initial results shows the expected performance, and the sense of security has been increased among the customers.

## Slide 5: Monitoring
The team members collects log when sensors are used and are constantly monitoring for any issues that comes the way.
Reports about different issues and fixes are sent to the product owners and team leaders daily.
So far, the progress is going according to the planned schedule.
The Feature expected to go live on June 1

## Slide 6: Variance Calculation
Status Report Ending Period 6
Sprint | %Complete | EV | AC | PV | CV | SV
1(Database & Sensor) | Finished | 4 | 4 | 4 | 0 | 0
2 (Image Processing) | Finished | 2 | 1.5 | 2 | 0.5 | 0
3 (Sensors Production) | Finished | 12 | 13.5 | 14 | -1.5 | -2
4 (Integration) | Finished | 2 | 1 | 1 | 1 | 1
5 (Testing) | Finished | 1 | 1 | 1 | 0 | 0
6 (Field Testing) | 30% | 3 | 2 | 3 | 1 | 0
Cumulative Totals |  | 24 | 23 | 25 | 1 | -1
Numbers presented are in Millions

## Slide 7: Project Closure
Support Team is set up to handle future minor issues that arises.
Final Report and User guide is created.
Each ATM will have a pamphlet showing the steps sticked in the room.
Resources are released after the project and are assigned for new project kick off’s

## Slide 8: Project Closure
Retrospective meeting is conducted: Documentation of valid changes needed and ideas to improve productivity is sent to upper management for consideration and implementation in relevant projects.
Team Evaluation and Feedback Survey is conducted for the purpose of self evaluation of strengths and weakness

## Slide 9: Thank You